## pmr
|  | ANNEX A | [18 empty] | ANNEX B
|  | Department of Budget and Management Annual Procurement Plan for FY 2006 | [18 empty] | (DepEd - Schools Division Office - Tagbilaran City Procurement Monitoring Report as of December 31,2021
Code (PAP) | Procurement Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Remarks (brief description of Program/Project) | PMO/ End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activity | [12 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IAEB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Contract Award | Contract Signing | Notice to Proceed | Delivery/ Accept | Payment Process |  | Total | MOOE | CO |  |  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| Repair and Rehabilitation of School Buildings (16 Classrooms, HE Building and Canteen) | [19 empty] | Tiptip ES | YES | Competitive Bidding |  | 11/20/19 | 11/28/19 | 12/18/19 | 12/18/19 | 12/18/19 | 12/18/19 | 12/18/19 | 12/18/19 | 9/22/20 | 9/28/20 | 5/21/21 | 5/25/21 | GoP | 6242170.91 | 6242170.91 |  | 5613375.27 | 5613375.27 |  | COA, Bohol Chamber of Commerce and Industry, Procurement Watch, PTA Federation | 11/20/19 | 11/20/19 | 11/20/19 | 11/20/19 | 11/20/19
| Repair and Rehabilitation of School Buildings (6 Classrooms, and Principal's Office) | [19 empty] | San Isidro NHS | YES | Competitive Bidding |  | 11/20/19 | 11/28/19 | 12/18/19 | 12/18/19 | 12/18/19 | 12/18/19 | 12/18/19 | 12/18/19 | 9/22/20 | 9/28/20 | 1/27/21 | 1/28/21 | GoP | 1965302.68 | 1965302.68 |  | 1829394.44 | 1829394.44 |  | COA, Bohol Chamber of Commerce and Industry, Procurement Watch, PTA Federation | 11/20/19 | 11/20/19 | 11/20/19 | 11/20/19 | 11/20/19
| Reproduction and Delivery of Modules from Kindergarten to Grade 11 | [19 empty] | All Elementary and Secondary Schools | NO | Competitive Bidding | 8/26/20 | 9/4/20 | 9/14/20 | 9/25/20 | 9/25/20 | 9/28/20 | 9/29/20 | 10/1/20 | 10/1/20 | 10/6/20 | 10/13/20 | 3/17/21 | 3/17/21 | GoP | 15730546 | 15730546 |  | 10235185.8 | 10235185.8 |  | COA, Bohol Chamber of Commerce and Industry, Procurement Watch, PTA Federation | 9/3/20 | 9/3/20 | 9/3/20 | 9/3/20 | 9/3/20
| Supply and Delivery of 6,348 reams of A4 ond Paper Substance 20 for Reproduction of Modules | [19 empty] | All Elementary and Secondary Schools | NO | Competitive Bidding | 1/12/21 | 1/18/21 | 1/27/21 | 2/8/21 | 2/8/21 | 2/8/21 | 2/8/21 | 2/8/21 | 2/15/21 | 2/24/21 | 2/24/21 | 3/11/21 | 3/11/21 | GoP | 1237937.88 | 1237937.88 |  | 867024 | 867024 |  | COA, Bohol Chamber of Commerce and Industry, Procurement Watch, PTA Federation | 01/18/2021 | 01/18/2021 | 01/18/2021 | 01/18/2021 | 01/18/2021
| Supply and Delivery of 7,375 reams of A4 ond Paper Substance 20 for Reproduction of Modules | [19 empty] | All Senior High Schools | NO | Competitive Bidding | 3/8/21 | 3/16/21 | 3/25/21 | 4/6/21 | 4/6/21 | 4/6/21 | 4/7/21 | 4/7/21 | 4/12/21 | 4/16/21 | 4/19/21 | 4/26/21 | 4/26/21 | GoP | 1437863.83 | 1437863.83 |  | 958750 | 958750 |  | COA, Bohol Chamber of Commerce and Industry, Procurement Watch, PTA Federation | 3/9/21 | 3/9/21 | 3/9/21 | 3/9/21 | 3/9/21
| Supply and Delivery of 5,296 reams of A4 ond Paper Substance 20 for Reproduction of Modules | [19 empty] | All Elementary Schools | NO | Competitive Bidding | 3/8/21 | 3/16/21 | 3/25/21 | 4/6/21 | 4/6/21 | 4/6/21 | 4/7/21 | 4/7/21 | 4/12/21 | 4/16/21 | 4/19/21 | 4/26/21 | 4/26/21 | GoP | 1032482.85 | 1032482.85 |  | 688480 | 688480 |  | COA, Bohol Chamber of Commerce and Industry, Procurement Watch, PTA Federation | 3/9/21 | 3/9/21 | 3/9/21 | 3/9/21 | 3/9/21
| Repair and Rehabilitation of Various School Buildings (14 Classrooms) | [19 empty] | Ubujan Elem School | NO | Competitive Bidding | 6/3/21 | 6/14/21 | 6/30/21 | 7/12/21 | 7/12/21 | 7/12/21 | 7/13/21 | 7/14/21 | 7/20/21 | 7/29/21 | 8/2/21 | 10/8/21 | 10/8/21 | GoP | 6594981.05 | 6594981.05 |  | 5011996.46 | 5011996.46 |  | COA, Bohol Chamber of Commerce and Industry, Procurement Watch, PTA Federation | 6/11/21 | 6/11/21 | 6/11/21 | 6/11/21 | 6/11/21
| Supply and Delivery of Nutri-Packs and Other ready-to-eat Foods for School Based Feeding Program SY: 2021-2022 | [19 empty] | All Elementary Schools | NO | Competitive Bidding | 9/3/21 | 9/13/21 | 9/22/21 | 10/4/21 | 10/4/21 | 10/4/21 | 10/4/21 | 2021-06-10 | 10/7/21 | 10/12/21 | 10/13/21 | 12/13/21 | 12/13/21 | GoP | 1781760 | 1781760 |  | 1781760 | 1781760 |  | COA, Bohol Chamber of Commerce and Industry, Procurement Watch, PTA Federation | 09/14/2021 | 09/14/2021 | 09/14/2021 | 09/14/2021 | 09/14/2021
| Supply and Delivery of 7,222 Reams of A4 Bond Paper Substance 20 for Reproduction of Modules | [19 empty] | All Elementary and Secondary Schools | NO | Competitive Bidding | 9/3/21 | 9/13/21 | 9/22/21 | 10/4/21 | 10/4/21 | 10/4/21 | 10/4/21 | 2021-06-10 | 10/7/21 | 10/12/21 | 10/13/21 | 10/22/21 | 10/22/21 | GoP | 1300000 | 1300000 |  | 967386.9 | 967386.9 |  | COA, Bohol Chamber of Commerce and Industry, Procurement Watch, PTA Federation | 09/14/2021 | 09/14/2021 | 09/14/2021 | 09/14/2021 | 09/14/2021
| Supply and Delivery of 10,025 Reams of A4 Bond Paper Substance 20 for Reproduction of Modules | [19 empty] | All Elementary and Secondary Schools | NO | Competitive Bidding | 9/3/21 | 9/13/21 | 9/22/21 | 10/4/21 | 10/4/21 | 10/4/21 | 10/4/21 | 2021-06-10 | 10/7/21 | 10/12/21 | 10/13/21 | 10/22/21 | 10/22/21 | GoP | 1804635.72 | 1804635.72 |  | 1342848.75 | 1342848.75 |  | COA, Bohol Chamber of Commerce and Industry, Procurement Watch, PTA Federation | 09/14/2021 | 09/14/2021 | 09/14/2021 | 09/14/2021 | 09/14/2021
[38 empty] | 0 |  |  | 0
[38 empty] | 0 |  |  | 0
Total Alloted Budget of Procurement Activities | [37 empty] | 39127680.92
Total Contract Price of Procurement Actitvites Conducted | [40 empty] | 29296201.62
Total Savings (Total Alloted Budget - Total Contract Price) | [37 empty] | 9831479.3
0N-GOING PROCUREMENT ACTIVITIES
| Repair and Rehabilitation of Various School Buildings (3 Classrooms and HE Building) | [19 empty] | Ubujan ES | NO | Competitive Bidding | 10/25/21 | 11/8/21 | 11/18/21 | 11/29/21 | 11/29/21 | 11/29/21 | 12/1/21 | 12/2/21 | 12/6/21 | 12/10/21 | 12/13/21 |  |  | GoP | 1582501.62 | 1582501.62 |  | 1580318.05 | 1580318.05 |  | COA, Bohol Chamber of Commerce and Industry, Procurement Watch, PTA Federation | 11/19/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021 | 11/19/2021
| Supply and Delivery of 26,454 Reams of A4 Bond Paper Substance 20 for Reproduction of Modules | [19 empty] | All Elementary and Secondary Schools | YES | Competitive Bidding | 12/13/21 | [12 empty] | GoP | 5026260 | 5026260
0
Total Alloted Budget of On-going Procurement Activities | [37 empty] | 6608761.62
[21 empty] | Prepared by: | [10 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
[21 empty] | JOHN ARIEL A. LAGURA | [10 empty] | CASIANA P. CABERTE PhD | [10 empty] | JOSEPH IRWIN A. LAGURA PhD
[21 empty] | BAC Secretariat | [10 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity

## Sheet1 (hidden)
Competitive Bidding | GoP | YES
Limited Source Bidding | Foreign | NO
Direct Contracting | Special Purpose Fund
Repeat Order | Corporate Budget
Shopping | Income
NP-53.1 Two Failed Biddings | Others
NP-53.2 Emergency Cases
NP-53.3 Take-Over of Contracts
NP-53.4 Adjacent or Contiguous
NP-53.5 Agency-to-Agency
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
NP-53.7 Highly Technical Consultants
NP-53.8 Defense Cooperation Agreement
NP-53.9 - Small Value Procurement
NP-53.10 Lease of Real Property and Venue
NP-53.11 NGO Participation
NP-53.12 Community Participation
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions
Others - Foreign-funded procurement